## Backlog
# | User Story | GitHub Issue | Assignees | Status | Description | Notes
Player
1 | 01.01.01 | 6, 68, 72 | Alex, Amirul, Kin, Matthew | Completed | As a player, I want to add new QR codes to my account. | check 5
2 | 01.02.01 | 5, 50 | Alex, Paul | Completed | As a player, I want to see what QR codes I have added to my account.
3 | 01.03.01 | 1 | Kin | Completed | As a player, I want to remove QR codes from my account.
4 | 01.04.01 | 2, 69 | Alex, Paul | Completed | As a player, I want to see my highest and lowest scoring QR codes. | check 2
5 | 01.05.01 | 3, 70 | Alex, Paul | Completed | As a player, I want to see the sum of scores of QR codes that I have scanned. | check 3
6 | 01.06.01 | 4, 71 | Alex, Paul | Completed | As a player, I want to see the total number of QR codes that I have scanned. | check 4
7 | 01.07.01 | 13, 66 | Matthew | In Progress | As a player, I want to see other player’s profiles
Game QR Codes
8 | 02.01.01 | 9, 65, 75 | Kin, Matthew | In Progress | As a player, I want to be able to scan QR codes and record a photo and the geolocation of the location or object.
9 | 02.02.01 | 21, 88 | Alex, Kin, Paul | Completed | As a player, I want to be able to comment on QR codes.
10 | 02.03.01 | 12 | Alex, Paul | Depracated | As a player, I want to be able to browse QR codes that I own. (2022-03-08: Deleted because identical to US 01.02.01) | check 12
11 | 02.04.01 | 22, 40 | Alex, Paul | In Progress | As a player, I want to be able to browse QR codes that other players have scanned.
12 | 02.05.01 | 19, 73 | Alex, Paul | In Progress | As a player, I want to see that other players have scanned the same QR code. | check 19
Player QR Codes
13 | 03.01.01 | 27, 45, 76 | Kin, Matthew | In Progress | As a player, I want to be able to generate QR codes so that other players can scan my QR code to see my game status.
14 | 03.02.01 | 26, 76 | Kin, Matthew | Completed | As a player, I want to be able to generate a QR code so that I can log in to another device with the same account.
Player Profile
15 | 04.01.01 | 34, 54, 57, 82, 86 | Alex, Matthew | Completed | As a player, I want a profile with a unique username and my contact information.
16 | 04.02.01 | 30, 44 | Kin, Matthew | Completed | As a player, I do not want to log into my application using a username and password as my device can identify me.
Searching
17 | 05.01.01 | 14, 86 |  | In Progress | As a player, I want to search for other players by username.
18 | 05.02.01 | 25, 74 |  | In Progress | As a player, I want to search for nearby QR codes by using geolocation.
Location
19 | 06.01.01 | 24 | Matthew | In Progress | As a player, I want to see a map of geo-locations of nearby QR codes.
Scoring
20 | 07.01.01 | 20, 22 | Alex, Paul | In Progress | As a player, I want to see game-wide high scores of all players. | check 20
21 | 07.02.01 | 17 | Alex, Paul | In Progress | As a player, I want an estimate of my ranking for the highest scoring unique QR code.
22 | 07.03.01 | 16, 17, 18 | Alex, Paul | In Progress | As a player, I want an estimate of my ranking for the total number of QR codes scanned. | check 18, 16
23 | 07.04.01 | 17 | Alex, Paul | In Progress | As a player, I want an estimate of my ranking for a total sum of scores of QR codes scanned.
Privacy
24 | 08.01.01 | 7, 8, 65 | Alex, Kin, Matthew | Completed | As a player, I don’t want the actual code recorded (e.g. so I can scan and score my vaccine passport). | check 8
25 | 08.02.01 | 7 | Alex | Completed | As a player, I want to be able to decline recording geolocation for privacy reasons.
Owner
26 | 09.01.01 | 8, 11 | Kin, Matthew | In Progress | As an owner, I don’t want to store big images online. | check 8
27 | 09.02.01 | 23 | Matthew | In Progress | As an owner, I want to be able to delete QR codes that are bad or malicious.
28 | 09.03.01 | 15 | Matthew | In Progress | As an owner, I want to be able to delete players.
Deliverables
N/A | N/A | 48 | Alex | In Progress | User Interface Mockups.
N/A | N/A | 49 | Amirul | In Progress | Storyboard Sequences.
N/A | N/A | 87 | Hannan | Completed | CRC Cards.
N/A | N/A | 42 | Hannan | In Progress | UML Class Diagram.
N/A | N/A | N/A | Everyone | In Progress | Sprint Plannings & Reviews.
N/A | N/A | 62 | Kin, Matthew | In Progress | Documentation.
N/A | N/A | 61 | Paul | In Progress | Unit Testing.
N/A | N/A | 63 | Kin | In Progress | Intent Testing.
Misc
N/A | N/A | 84 | Kin | Completed | Loading QRCode and Image into EditQRCodeScreenActivity.
N/A | N/A | 77 | Amirul | In Progress | Write all XML files.
N/A | N/A | 64 | Alex, Kin, Matthew, Paul | Completed | Implement QRCode class.
N/A | N/A | 60 | Matthew | In Progress | Implement Admin class.
N/A | N/A | 58 | Paul | Completed | Implement navigation bar component.
N/A | N/A | 56 |  |  | Basic UI for the Edit Account page. | check 56
N/A | N/A | 55 | Alex, Hannan |  | Player class (design update). | check 55
N/A | N/A | 53 | Alex | In Progress | Create Account input format (to be checked using regular expressions).
N/A | N/A | 52 | Kin, Matthew | Completed | QR hashing and score implementation.
N/A | N/A | 51 |  |  | Basic UI for viewing a Player Profile. | check 51
N/A | N/A | 39 | Matthew |  | Basic UI for the Map page. | check39
N/A | N/A | 36 | Kin, Matthew | Completed | Implement basic Mapping features.
N/A | N/A | 32 | Amirul, Matthew |  | Basic UI for the Login w/ Email page. | check 32
N/A | N/A | 31 | Amirul, Matthew |  | Basic UI for the Create Account page. | check 31
N/A | N/A | 29 | Alex, Hannan, Kin, Matthew, Paul | Completed | Implement Player class.
N/A | N/A | 10 | Alex | Completed | Implement the firestore database.